## Actions for 2019-2022
| HR Excellence In Research Action Plan |  |  |  |  | COMPLETE
Link to Principles and previous HR Excellence in Research submission: http://www.leedsbeckett.ac.uk/research/hr-excellence-in-research-award-for-leeds-beckett/ | [5 empty] | Live - On Schedule
Last Reviewed: 29 April 2020 | [5 empty] | Planned - not started/not due
ACTIONS FOR 2019-21 | [5 empty] | Behind Schedule - low priority
Behind Schedule - high priority
Action number | Action | Responsibility | Deadline | Success Criteria/Outcome Measures | Links to other Strategies/Action plans | Status | Comments
Principle 1: Recognition of the importance of recruiting, selecting and retaining researchers with the highest potential to achieve excellence in research.
1.1 | Require gender-balanced shortlists for all senior academic recruitment where search agencies are used. | Human Resources | December 2020 | Gender balanced shortlists received from search agencies (leading to an increase in the number of women in senior roles). | Gender Pay Gap Report 2018 | COMPLETE | 45% female shortlisted candidates Dixon Walter is the search agency used and they have provided data for past/current recruitment campaigns for senior roles since January 2020 (gender, ethnicity, sexual orientation, disability). The 14 senior roles include Head of Subjects and a Professor. All shortlists received except 1 included both male and female candidates and across the 14 roles, there were 45% female shortlisted candidates. As detailed in our latest Public Sector Equality Duty Report (2021), female representation at senior level (grade 10 and above) has increased from 43.27% in 2018 to 46.74% in 2020. https://www.leedsbeckett.ac.uk/our-university/equality-and-inclusion/equality-data/
1.2 | Complete a review to understand the experience of female applicants to research positions, and identify any barriers to applicants. This will include a review of job descriptions and shortlist criteria for terminology or phrasing which may be a barrier. | Human Resources | December 2020 | Review completed and recommendations for action implemented. Longer term aim to increase in the number of female applicants applying for academic (including research) positions to achieve a 50:50 Male/Female balance (in 2018/19 42.21% of applicants for academic positions were female and 46.27% of applicants for research positions were female). | Athena SWAN | COMPLETE | Trialling a guide on inclusivity HR Services have promoted the jobs page Diversifying.io to recruiting managers in Schools and Services as a potential place to advertise vacancies and “connect job opportunities to people from underrepresented talent pools” (13 posts have been advertised on this site to date, including 8 lecturer/senior lecturer posts). The success of this approach will be analysed over the next 6 months. In addition, a guide for Schools/Services on inclusivity in advert wording/promotional materials to improve attraction of female candidates is being trialled with recruiting managers in the School of Built Environment, Engineering and Computing (as a School with a proportionally low number of female academics). Following this trial, it is intended to share the guide more widely across the University. The guide includes tools to analyse advert/job description wording for gender bias and suggests different job boards to attract female applicants. There is also an Athena SWAN subgroup is focussing on career development and progression (Athena SWAN submission for institutional award in May 2022 - see section 6 below). As detailed in our latest Public Sector Equality Duty Report (2021), whilst the proportion of female applicants for academic roles dropped to 37.5%, female candidates are proportionally more successful as they progress through the recruitment process with the proportion of female shortlisted candidates rising to 44.1% and the proportion of female appointed candidates rising to 48.7%.
1.3 | Ensure shortlisting and interview panels are diverse in composition. | Human Resources | July 2020 | Monitoring of recruitment panel membership in place and analysis/report on a 6 monthly basis. | Gender Pay Gap Report 2019 Race Equality Charter | COMPLETE | New recruitment and selection training has been rolled out We have prioritised the updating of our recruitment and selection training for panel members to contribute to fairness, consistency and the best assessment of the candidates’ potential in our recruitment processes. Interview panel composition is recorded on our iTrent HR system (and these records have enabled HR to identify colleagues who regularly interview). The new training has been rolled out to these panel members for completion by July 2021. In addition to guiding managers through our recruitment and selection processes, the new training challenges prospective panel members to consider how to make their approach to recruitment more inclusive, how unconscious bias might impact on how appointments are made and what steps they can take to remain as objective as possible. So far 334 colleagues have been enrolled on the training, including 91 academic colleagues. There is good gender diversity in the pool of colleagues enrolled on the training - with a 58%/42% female/male split. 7% of those enrolled have declared that they are from a Black and Minority Ethnic background. Equality, Diversity and Inclusion dashboards have been developed in Tableau and will be made available to senior colleagues in Schools/Services in 2021. These include EDI staff profile and recruitment data, which can be manipulated and filtered by the report user.
Principle 2: Researchers are recognised and valued by their employing organisation as an essential part of their organisation’s human resources and a key component of their overall strategy to develop and deliver world-class research.
2.1 | Modernise our approach to performance development to enhance individual and team performance, including increased manager skills for effective performance management conversations. Provide specific guidance so that the research community can engage effectively with the performance development review process | Human Resources | May 2021 | • Objective setting and development plans for those engaged in research linked to our organisational research strategy. • All reviewers have accessed training on good quality performance conversations. • Colleague survey results indicate that the research community have clear objectives and focused development plans • Guidance developed with and for the Research Community published on the intranet. | People Strategy | Complete | New PDR website launched with new resources Development support on how to have effective PDR conversations was put in place for reviewers and reviewees in time for the 2021 cycle, including live webinars and online resources and guidance. We have refreshed our PDR approach to focus on 4 pillars for a good quality of conversation, with a focus on feedback, outputs and objectives. We launched this on a new PDR webpage that has received over 1200 hits. We sent targeted communications about this to Heads of Subject and Course Directors signposting PDR support for academic and research colleagues. A recorded version of the session for PDR reviewees is available on the intranet for colleagues to access at any time. Our People and Organisational Development (POD) team have worked in collaboration with academic and research colleagues to provide resources to better support academic and research PDR conversations e.g. self-reflection guides, which covers key themes in research contributions and example questions for an effective conversation, dependant upon the stage of the individual's research career. The POD team have also provided a bank of teaching and research example objectives. The documents have been validated by a Professor who is external to Leeds Beckett University, in the role of critical friend. The POD team also consulted with the Director of Research and Enterprise to signpost to some key external research sources to inform effective PDR planning. A Performance Management Masterclass ran in May 2021, targeted at grade 6-9 managers (inc. academic & research managers) - 65+ colleagues attended. A managing performance toolkit has been developed that pulls together all aspects of performance management resources available. This was communicated via Deans and Directors and with the Employee Relations team to operationalise with managers. A new manager session on performance management has been piloted and dates for further sessions will be made available to managers across the University. A new performance management e-learning module launched in March 2021 with some specific references to managing objectives for research outputs. The University-wide pulse survey in 2021 focussed on colleague wellbeing, and so feedback on colleague views of PDR is not available from this source. Our new Colleague Survey launched in November 2021, with the results due in early-2022. The purpose of the survey, which will run annually, is to seek feedback on a number of different aspects relating to how colleagues experience working life here at LBU and connect to how we measure various aspects of our new university strategy over the next 5 years. The survey includes a number of questions relating to leadership and management, the results of which will indicate whether the research community have clear objectives and focused development plans - 'I can see how I contribute to the University aims and strategy', 'I receive regular and developmental feedback on my performance', 'I feel supported to develop in my role', and 'I have had a PDR conversation in the last 12 months.'
2.2 | Academic staff (including Researchers) will be actively encouraged by managers to take up promotion opportunities through the annual PDR process. | Deans of School and Heads of Subject | December 2020 | All academic staff (including Researchers) to have discussion of career development and promotion annually as part of the PDR process. | Athena SWAN Race Equality Charter | Complete | New PDR approach and resources The POD team have refreshed our PDR approach to focus on 4 pillars for a good quality of conversation, with one of the pillars of the conversation focussing on career and development planning. We have reviewed our guidance to support better PDR conversations. The new PDR webpage also signposts to peer feedback support available through our Centre for Learning and Teaching and key external website research resources. The resources encourage reviewers to tailor the conversation based on some of the different stages of a researcher's career. Specific academic PDR webinars concentrate on the importance of career development and planning discussions as part of the PDR conversation, with direct signposting to supporting resources. The new approach, resources and webinars were communicated via all colleague emails and specifically targeted emails to academic PDR reviewers.
2.3 | We will review our academic career pathways, including teaching and learning, research and enterprise. We will continue to enhance the use of developmental roles including the use of Graduate Teaching Assistants. We will record and review the career development and progression of our research community. | Human Resources | July 2021 | Clear career pathways in place and supported by published guidance, information and other development resources for colleagues that support career progression . Representation of women within the Professoriate to rise to 35% by 2021. Data shows career development and progression at all levels within the research community. | People Strategy | Complete | Female representation within professoriate has increased As reported in our Public Sector Equality Duty Report (2021), the female representation within the professoriate has increased from 27.69% in 2018 to 32.73% in 2020. 349 places on our POD webinar sessions between March and November 2020, including keynote talks, network events and open programme sessions, were taken by academic colleagues. On 4th February 2020, we held a Network Event for Heads of Subject and Course Directors - "Building our research culture through research-teaching practice nexus" (four internal speakers and table discussions). On 21 June 2021 we held a Network event for Heads of Subject, and Deans, led by the Deputy Vice Chancellor (Research and Enterprise), around making best use of the Professors in our Schools. In 2020, a Development and Training website - https://teachlearn.leedsbeckett.ac.uk/development-and-training/- was developed to bring the development and training available across the University together in one 'programme', to ensure colleagues can easily access the development they need. The programme is organised into six categories - Research, Educational Enhancement, Professional Practice, Support, Community and Innovation. 3 Academic colleagues currently undertaking an ILM Coaching Programme qualification - 1 has passed so far as at November 2021. 19 Academic mentors are part of our internal network of experienced mentors and coaches (for general mentorship around leadership/career development) - 22 academic mentoring relationships have been established since September 2020. 9 academic colleagues have volunteered to become diversity mentors, with 2 training webinars and facilitated discussions held in March and September 2021 as part of our pilot diversity mentoring for transitions through leadership scheme. An MS Teams channel was created in August 2021 as a collaborative space for academic colleagues to connect with other colleagues across the University and share mentoring best practice, tools and peer support. The internal Research Team Leadership programme was completed in October for 4 Professors and 12 Readers representing all of the Schools. The programme was evaluated very highly and one delegate is continuing their development process with a coach from our internal coaching pool. If appropriate the programme will run again following the next academic promotions round in 2022. 8 academic coaching relationships have been established in 2021 and an MS Teams has now been created as a collaborative space for academic coaches to connect with our coaching network, sharing coaching best practice, tools and peer support.
aSK POD - Julia to speak with Paul
3.1 | Deliver sessions on ‘Research Impact’ and ‘Public Engagement’ once a term, recognising different levels of researcher experience in content. Promote to FTCRs at induction and to ECRs via DoRs, Centre Heads and R & E Coordinators at School level | Graduate School Directors of Research | July 2021 | Increased attendance recorded via i-Trent. Maximum cohorts attending (depending on workshop size) | Staff Development Programme | In progress/Carry forward to 2022/24 plan | New training programme launched – with more sessions in progress The Research & Enterprise (R&E) Staff Development & Training programme was redeveloped in 2021/22 with a strong focus on researcher development. There has been a notable increase in registrations at development sessions since October 2021 - with a good portion of attendees being ECR and FTCRs. Following our 2021 REF submission, it has become clear that the university needs to further enhance its training to researchers specifically in relation to research integrity and impact. We have committed to doing this by creating a new Research and Knowledge Exchange (KE) Academy which will provide a comprehensive development programme to all academic staff - with a specific focus on research active staff, providing development pathways for each stage of their research journey. This also ties in with a priority action in our KEF Concordat and HEIF accountability statement that we will invest in the development of our staff to deliver enhanced research, impact and KE. Lessons learned from the REF submission will form new development opportunities around Research Impact via interactive workshops and online toolkits in addition to sessions on Research Integrity, Public Engagement and other complimentary development programmes. This includes new online training sessions which will be provided by Walcott Communications: ‘Integrating Impact into Your Everyday’ – a five-module course for early and mid-career researchers and those new to impact; and ‘Building Impact Literacy’ - for more experienced researchers. Additionally, we have commissioned a researcher development support programme from Vitae to embed the objectives of the Research Excellence Framework (REF) in the culture of the university. This includes which includes sessions on engagement, influence and impact, and train the trainer support to enable us to deliver training in-house. All programmes will continue to be promoted and communicated to all new colleagues at their induction, and through our MS Teams channel, e-newsletters and through Directors of Research, Centre heads and R&E coordinators in schools.
3.2 | Continue to deliver 'PGR Mental Health and Wellbeing' workshop within our Research Awards Supervision (RAS) training day, flag up at Experienced Supervisor workshops and deliver stand-alone workshop twice yearly. | Graduate School | July 2021 | Open lines of communication between staff supervising PGRs, staff acting as PIs and appropriate wellbeing services within the University | Strategic Framework for the Wellbeing and Mental Health of our Colleagues | In progress/Carry forward to 2022/24 plan | New framework for mental wellbeing is in progress We have been running our Experienced Supervisor workshop twice a year – with five members of staff attending in 2019 across two workshops; 14 attending in 2020 across two workshops; and eight in 2021 attending one workshop. Feedback received in June 2020 showed 100% satisfaction, and in May 2021 showed 92% satisfaction - and we will continue to deliver this workshop twice a year. The workshop is promoted through our newly developed R&E staff development and training intranet pages, the new MS Teams group for our research community, the LBU Voices all staff e-newsletter, and internal marketing campaigns. Delivery of the ‘PGR in Mental Health and Wellbeing’ workshop has been delayed due to lack of availability from the facilitator, owing to a reduction in their contract. Discussions are continuing to confirm dates for the 2021/22 development programme. This will be solidified in 2022 as a framework for mental wellbeing will be incorporated as part of our supervisor training. A new mental health and wellbeing workshop for all research students is in development and will be offered through the Library and Student Services team following the students’ induction period.
3.3 | Include support for MRes Students as explicit aspect of RAS training sessions | Graduate School Researcher Development | November 2021 | A 10% increase in MRes completions. | Staff Development Programme | In progress/Carry forward to 2022/24 plan | New Academy will support MRes students We updated our MRes student handbook in 2021. The MRes is specifically mentioned, along with all types of research degree that we offer, as part of the training around 'The Student Journey', within our Research Awards Supervisor workshop. The university recognises that our MRes students need to be specifically addressed in our training, development and support offered. This action point is ongoing as the creation of our new Academy will support this need and we will continue to redevelop this programme – as will our current process of instigating change and improvements within the Graduate School.
3.4 | Refresh the RiSK training package run by R&E Services on applying for research funding in line with CROS and PIRLS feedback to cover small bid applications through to PI responsibilities as appropriate. | Graduate School R&E Services | December 2021 | 5% increase in applications for external funding | Research & Enterprise Strategy 2016-2021 | Complete | New training developed to support grant application process Our RiSK programme has been developed over 2010/21 and the new programme was delivered online in March 2021 – with 15 staff attending, and an 88% satisfaction rate; and in October 2021 with 6 staff attending, and an 80% satisfaction rate. The redeveloped programme includes information about small bid applications; and a dedicated RiSK webpage has been created on the staff intranet. The workshop will continue to run on a twice-yearly basis, with online resources and toolkits available on the intranet. It will continue to be refined to further develop research skills. So far, nine funding applications have been written by researchers, with support from the R&E team, following attendance at the workshops; and relationships have been created and strengthened between the Research Development Managers and research-active colleagues. Feedback has been very positive, with one researcher who attended the workshop in March 2021 saying: "You demystified the language used in these applications, which was a real help to me."
3.5 | Encourage ECRs to undertake Research Awards Supervision (RAS) training and to submit CV for approval where appropriate | Directors of Research/Postgraduate Research Tutors at School and Unit level | August 2021 | Increase in applications for approval as Advisor and Supervisor (where appropriate) at URDSC | Research & Enterprise Strategy 2016-2021 | Complete | New online toolkits to support supervisor training – and redesign of training programme planned for 2022 Starting in June 2021, all new academic starters are now contacted via a welcome email from the R&E service, with an introduction to the R&E development and training programme. New starters are also informed about the development and training opportunities at their induction, via a presentation and Q&A session. The Research Awards Supervisory (RAS) Programme is highlighted within this communication to all new starters. Directors of Research and Research Co-ordinators also actively encourage all new research staff - specifically ECRs - to submit their CVs for approval to become a Supervisor. The Graduate School has approved 70 CVs in the last two and a half years - 30 in 2019/20, 30 in 2020/21, and 17 in the academic year 2021/22 up to November 2021. This number will increase before our final submission in February 2022. We have developed online toolkits for our RAS programme to enable prospective supervisors to undertake the training in their own time. Since this was introduced in September 2021, 55 colleagues have received the online toolkits (28 Becoming a Research Supervisor, nine Preparing for Annual Progression, nine Becoming an Independent Chair, and nine Preparing for Confirmation of Registration) - and feedback has been positive. The RAS training programme will undergo a complete redesign in 2022 in order to bring it in line with the Student Admin Manager (SAM) system and the updated Academic Regulations, specifically the Research Award Regulations.
Principle 4: The importance of researchers’ personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career.
4.1 | Support all members of academic staff to indicate individual research plan, appropriate to their role, as part of annual PDR process | Directors of Research / Deans of Schools / Heads of Schools | May 2021 | School level reporting on resources allocated for support for research development across academic staff post PDR annual cycle | People Strategy | Complete | New PDR resources launched We have focused on raising awareness of the fundamental principles of PDR and emphasising meaningful conversations around objectives, outputs and development planning. We have offered 4 tailored webinars specifically for academic colleagues (reviewer and reviewees). We have designed a new suite of resources for academic colleagues, hosted on a new PDR webpage. These resources were developed in consultation with LBU peers and an external academic consultant, and include sample academic objectives and outputs and a self-reflection and planning guide for reflecting on research contributions The new resources and webinars were communicated via all colleague emails and specifically targeted emails to academic PDR reviewers. Feedback on the academic reviewer PDR webinars has been very positive.
4.2 | Increase numbers of academic staff engaged in research mentoring | Directors of Research / Graduate School/HR | May 2021 | 10% increase in staff with mentoring agreement in place | Research & Enterprise Strategy 2016-2021 | COMPLETE | Sharing best practice to develop mentoring in all schools As part of our Knowledge Exchange (KE) strategy, which aligns with our university’s five-year strategic plan for 2021/22 – 2026/27, we are committed to ensuring that every colleague develops a five-year research and KE plan, to be reviewed annually, and that every colleague will be appointed a mentor at Professor or Reader level. There is currently a mentoring scheme in every school, with every school having a dedicated coordinator for mentoring. Going forwards, all schools will be implementing a more structured and standardised approach to mentoring so that this is consistent across all areas of the university. The new R&KE Academy will be working with all mentoring coordinators to ensure that they are all fully aware of the training and development available to researchers and passing this on to mentors. An example of best practice for mentoring in our schools is the Leeds School of Arts (LSA): In addition to a ‘buddy’ scheme for all new starters in the school, and the promotion of the wellbeing programmes offered by HR, the LSA team have established a research mentoring programme which focuses specifically around providing peer support to ECRs, colleagues working towards achieving independent researcher status, or aspiring for promotion to Reader. The programme consists of three hours of mentoring over the course of six months. It includes opportunities to build networks, learn from one another, and focus on professional development. Mentees are matched with a Senior Researcher within the school – they are able to express who they would like to be matched with, if that colleague has availability, or they can discuss their aspirations and goals with their DoR to help identify the most suitable mentor. Advice and guidance is made available for both mentors and mentees from the school’s Support, Enterprise and Outreach team. Mentees can request to re-join the scheme at any point in their career at LSA and can request to work with either the same mentor again or expand their network and work with someone new. We will be using this example of best practice to develop the mentoring offerings across all schools.
Principle 5: Individual researchers share the responsibility for and need to pro-actively engage in their own personal and career development, and lifelong learning.
5.1 | Support Early Career Researchers to gain Independent Researcher Status (LBU REF 2021 Code of Practice) | Directors of Research, Heads of Subject and R&E Coordinators | July 2021 | 5% increase in Independent Researcher figures | People Strategy/Research & Enterprise Strategy 2016-2021 | In progress | IRS procedure being updated in 2022 As part of our KE strategy for 2021/22 – 2026/27, we have committed to increasing our percentage of colleagues who are independent researchers with significant responsibility for research to 80%. Our plans for supporting ECRs to gain IRS status include our communications plan, clear development pathways and the development of online resources. Our IRS procedure is being updated following our REF submission – and updated instructions will be publicised and supported through workshops and our online resources. This will be accomplished during 2022. We can confirm that, in REF2014, we entered 220 staff with independent researcher status; and in REF2021, this increased to 414 staff. This is an increase of 88%.
5.2 | Provide annual workshops detailing expectations for promotions to senior research roles | DVC (Research & Enterprise) | January 2020 | An increased number of successful women applicants. Representation of women within the Professoriate to rise to 35% by 2021. | People Strategy and Research & Enterprise Strategy 2016-2021 | complelete | Female representation at senior level increased to 46.74% Our Vice Chancellor delivered academic promotion workshops in the January of 2020 and 2021, with results being announced in June of each year. In 2020, four colleagues were promoted to Professor (including three women), and eight were promoted to Reader (including four women.) In 2021, six colleagues were promoted to Professor (including two women), and 10 were promoted to Reader (including six women). This equates to a 33% increase in promotions awarded to colleagues – and a 14% increase in successful applications for women colleagues. As detailed in our latest Public Sector Equality Duty Report (2021), female representation at senior level (grade 10 and above) has increased from 43.27% in 2018 to 46.74% in 2020. https://www.leedsbeckett.ac.uk/our-university/equality-and-inclusion/equality-data/
5.3 | Refresh Research Development Programme and signpost for ECRs, Mid-career and PIs where appropriate | Graduate School | December 2020 | Targeted approach in place and publicised. Monitoring of attendance by gender and positive action statements and academic role of attendees | Research & Enterprise Strategy 2016-2021 | Complete | New training programme launched The R&E Development and Training programme was redesigned in 2021. The programme is structured around the following themes: research; enterprise and knowledge exchange; research supervision and research impact; management and leadership. The programme provides of a suite of workshops and online toolkits to support academic staff in all stages of their research careers. Some opportunities will be tailored specifically to the individual career stages of our research and enterprise staff in order to reflect their development needs. This will continue to be developed in the 2021/22 training programme. Individual training sessions have positive action statements with the purpose of highlighting who they will benefit. ECRs, FTRs and Mid-Career researchers are signposted to the programme through our newly developed R&E Staff Development and Training intranet pages, the new MS Teams group for our Research Community, LBU Voices and internal marketing campaigns.
5.4 | To run a pilot scheme to support five members of staff to obtain the UKCGE Supervisor Recognition. | Graduate School | August 2021 | The pilot scheme will be run over academic year 2020/2021. Success will be for five researchers to obtain recognition. The outcome of the pilot will be reviewed and rolled out. |  | Complete | The scheme ran in 2021 and will run again this year Five members of staff were nominated to apply to the UKDGE Supervisory Accreditation programme in 2021, with one member of staff submitting an application in October 2021. We received a lower number of applications than we wished due to the extenuating circumstances around the pandemic - academic colleagues were continuing online teaching in early 2021 and then moving focus to in-person teaching in September 2021. We will offer to sponsor another five supervisors in the 2022/23 financial year; and the outcome of this year’s applicant’s submission will be announced in February 2022.
5.5 | Develop a communication strategy for disseminating and celebrating successful outputs of FTCRs and ECRs | Graduate School / Library | August 2021 | FTCRs and ECRs Symplectic presence. 20% increase in social media use communicating success and recognition. | Staff Development Programme | COMPLETE | New communication channels created to celebrate success The R&E service has developed a comprehensive communications strategy over the past year, to support our research community. We have created a number of new communication channels in order to share and celebrate successful research outputs both externally and internally. We have established a new MS Teams channel for the LBU research community, which currently has 232 members. The group was created to provide our community with a place to share their outputs and successes and learn about new development, training and funding opportunities. We set up a new Twitter account in September 2020 for the R&E team to share news of the research and enterprise activities taking place across the university. The account now has 473 followers and actively follows researchers across the university at all stages of their careers and seeks to regularly share their posts around new studies, publications and collaborations as well as our own press releases. Successes are also shared via: a quarterly research and enterprise newsletter, which is distributed to all staff at the university; the university’s news website and school blogs; press releases; the central communications team’s all staff e-newsletter LBU Voices; the VC’s daily news email to all staff; and our own and central communications’ social media channels. Directors of Research (DoRs) also support communications with their schools by flagging communications with their FTCRs and ECRs. The number of research outputs recorded in Symplectic for ECRs was: 2019: 140; 2020: 126; and 2021: 170. For FTCRs this was: 2018: 131; 2019: 101; 2020: 80; and 2021: 76.
5.6 | In response to CROS 2019 pilot targeted induction for new FTCRs in line with Concordat revised principles and disseminate materials to ECRs across the University. | Graduate School | January 2021 | Record of meetings and TNAs for FTCRs with Graduate School Staff Researcher Development team |  | Complete | Communications plan targets new FTCRs and ECRs- and examples of best practice in schools We have created a communications plan which will target new FTCRs and ECRs, including providing information at induction about the development and training programme, and wider university support that is available to them. We record all individuals who take part in an induction – which includes receiving information about the training and development programme. This is also discussed with all researchers as part of their PDR process. Additionally, there are strong examples of best practice across the university schools – one example is the Leeds School of Arts (LSA), who deliver a very helpful induction programme for ECRs: The school undertakes a full induction with each researcher - including a training needs analysis – followed by training in areas such as Open Access, guidance in completing individual five-year research plans, and training around understanding impact and how it relates to practice-led arts. Colleagues who do not have a PhD are provided with information on how to undertake one. Mentoring is actively encouraged, and each individual is paired with a mentor via their DoR. The school issues a monthly research newsletter and has a Research Support Teams community – which includes channels for academic promotions information and specific information and discussions for Readers and Professors. The school also hosts a website to promote and celebrate all its research outputs in an accessible manner: www.leedsbeckett.ac.uk/research/larc/outputs/ The R&E development team will also be creating ‘development pathways’ to support researchers in all schools, across all career stages - and these will be promoted to researchers accordingly.
5.7 | Inform all staff registered for Research Awards of refreshed Researcher Development Programme and highlight ECR support. | Graduate School | January 2021 | Engage with at least 10 ECRs / FTCRs to develop a communication plan to develop and deliver career development workshops. |  | Complete | Developing support for ECRS and FTCRs through our training Within our researcher development programme, we clearly highlight who each training course is suitable for - eg. ECRs, mid-career researchers, etc. This is made clear on both our intranet pages for the programme and on each individual course's Eventbrite booking page. ECRs will be able to view our programme on the intranet and clearly view which programmes are aimed specifically at supporting them. All staff who are registered for research awards at the university receive regular updates about upcoming training and development courses on a regular basis: this is promoted via our all colleague quarterly research and enterprise newsletter, the bi-monthly all colleague LBU Voices newsletter, the MS Teams researcher community channel and the intranet. So far, more than ten FTCRs and ECRs have engaged with us by attending workshops in 2021/22. We will run a training and development needs survey in March 2022 for all research staff - one survey for postdoctoral and ECRs and one for MCRs and more established researchers - to gather further evidence for this action point and to provide us with a baseline for further development of support for ECRs and FTCRs as part of our new action plan.
5.8 | Roll out mandatory online training ‘Academic Integrity’ module for all new research staff. | Graduate School | May 2021 | Monitor take up via People Development online. 100% enrolment by new FTCRs |  | In progress | New training through Vitae in development We have been unable to meet this action as described – as it is not possible to make a course mandatory as per our university’s regulations. However, we have a 20 minute Academic Integrity module which is available to colleagues. We promote this regularly through our intranet pages and communications around our training programme (internal newsletters and MS Teams channel). 23 members of academic staff have completed the module between 2019 and 2021. A UKRIO Research Ethics training event took place at the university in November 2021, and encompassed research integrity. Due to the impact of Covid, and financial restraints, we have not yet established a dedicated module around Academic Integrity. We plan to address this through a proposal developed by Vitae; and this will form part of the strategy of our new Academy.
Principle 6: Diversity and equality must be promoted in all aspects of the recruitment and career management of researchers.
6.1 | Race Charter working groups to propose and lead on developments and enhancements needed to better support race equality (diverse academic, and within that, research, community). Full review of the Athena SWAN action plan ready for institution resubmission, including consideration and analysis of our research community profile. | Human Resources | Submission 2021 | Achievement of Race Equality Charter Bronze Award Retention of Athena SWAN Award |  | In progress | New submission date for Athena SWAN – May 2022 Due to Covid-19, we have agreed a revised submission date of May 2022 for our Athena SWAN Institutional award. The Self-Assessment Team (SAT) and subgroups are in place and meeting regularly. Similarly, we have agreed a revised submission date for the Race Equality Charter Bronze Award of February 2023. A number of focus groups were held in January 2022 to help inform the University’s understanding and plans for advancing anti-racism and improving gender equality. The sessions were facilitated by postgraduate research students and explored issues such as gendered and racialised career barriers - and also broader questions, such as understanding colleague and student perceptions of LBU as an anti-racist organisation. These focus groups will help us ensure diverse voices are informing our work on race and gender equality across Leeds Beckett.
6.2 | Monitor the recruitment and selection, and academic promotion process to develop greater understanding of how different applicant groups progress, and identify the different success rates of different groups. Use this data to develop strategies that will enhance progression rates for groups where this is different to the majority group. | Human Resources | December 2021 | Data set developed that identifies sucess rates at application, shortlisting and appointment for different groups. Using data develop strategies, and set specific targets to improve success rates and apply them in specific Schools to improve outcomes. | Athena SWAN Race Equality Charter | In progress | Continuing our development of new interactive reports using Tableau As one of our Equality, Diversity and Inclusion (EDI) priorities we are using Tableau to develop the analysis and dissemination of our workforce and recruitment data to derive greater insights. These interactive reports have the potential to transform the knowledge we have of our workforce and its diversity to guide EDI action planning in the future, both at University and School/Service level. This data will be used to develop strategies to improve success rates (including via our Athena SWAN career development and progression subgroup and Race Equality Charter colleague subgroup). Work on this action will continue, and it will be included in our 2022-24 Action Plan.
6.3 | Embed wellbeing content in mandatory health & safety training and resources for managers (including new managers) to promote good mental health and wellbeing through the effective management of workloads and people. | Human Resources | September 2020 | • All new colleagues to complete mandatory online health & safety training • 600+ unique views of wellbeing staff webpages • During 2019/20, 75 managers to attend a Manager Matters development session which includes consideration of wellbeing (Team Wellbeing session, Being a manager at LBU, Team strengths and Effective team meetings and 1:1s) | Strategic Framework for the Wellbeing and Mental Health of our Colleagues | Complete | New wellbeing resources created Since September 2020, there has been a greater focus on wellbeing as part of our colleague development offer, including webinars, newsletters, communications and signposting. 465 colleagues are members of the Wellbeing and Mental Health Network, acting as advocates. LBU participated in Mind's Mentally Healthy Universities project during the 2020/21 academic year, piloting interventions to open up conversations about mental health and reduce stigma. Colleagues in Leeds School Arts and School of Sport, including managers and academics, were trained as Mental Health Champions and Peer Supporters, gaining the knowledge and skills to continue in these roles. We have developed a range of new resources, including managers' guides for having wellbeing conversations, highlighting wellbeing in one-to-ones, a comprehensive list of internal and external resources to support colleagues experiencing mental health difficulties, and a revised Wellbeing Action Plan. Wellbeing-focused sessions have been delivered to 30 academic staff in the Leeds Business School and 25 staff in the School of Events, Tourism and Hospitality Management. A Wellbeing session was included in the programme for the DEAP conference in June 2021, aimed at all academic colleagues. There have been regular university-wide communications promoting good mental health, such as for National Work Life Week in October 2021.
Principle 7: The sector and all stakeholders will undertake regular and collective review of their progress in strengthening the attractiveness and sustainability of research careers in the UK.
7.1 | Human Resources and the Graduate School/Research and Enterprise Services will report on the progress of the HR Excellence in Research Action Plan within the Annual Research and Enterprise Report. This report will be presented at the October meeting of the University Research and Enterprise Committee and the relevant section and minutes will be available online. | Human Resources and Graduate School/Research and Enterprise Services | 2021-07-01 | Good progress reported against the action plan. | People Strategy | Complete | Annual progress updates have been reported Annual updates on the progress against the action plan are made by report to the Research and Enterprise (R&E) Committee meeting. The R&E Committee is responsible to the Academic Board for overseeing our university’s research, enterprise, other scholarly activity, and the provision of research degrees. The report provides an overview of the progress made on the actions listed within the plans. It is created jointly between People Services and Policy (HR) and the Research & Enterprise Services (R&E) Development and Training team. The report reviews our progress on the actions within the plan, provides a list of key achievements, and any potential risks to our overall achievement. Reports have been submitted in January 2020, January 2021 and January 2022.
7.2 | Use the CROS & PIRLS survey outcomes, subsequent national surveys as well as the evidence-based outcomes taken from the Senior Lecturers on the Research Degree Sub-Committee to inform researcher development and the Action Plan. | HR/Graduate School/Research and Enterprise Services/Schools | 2021-05-01 | R&E actions from the surveys and the feedback from the RDSC membership scheme informs researcher development support at appropriate levels. The development needs recorded in PDR and deployment meetings. |  | Ongoing - will be continued into next year | New training programme launched – and preparations for CEDARS 2023 As a university, we use all of our survey outcomes, including CROS and PIRLS, colleague surveys (including our own internal survey which we plan to deliver in early 2022) and national surveys to develop the support and training programmes that colleagues require. As a result of feedback through surveys, we have redeveloped our programme in 2021. We are significantly investing in the development programme through our new Academy, as per our HEIF accountability statement. We have taken on board the areas of interest for development that have been expressed by our colleagues in the CROS 2019 survey. All managers of researchers are encouraged to discuss and document their development needs as part of their annual PDR meetings, and a good deal of support and guidance is provided by HR for this purpose. The Research Degrees Sub-Committee has implemented a competitive membership scheme, which saw four senior lecturers on a two-year tenure sitting on the committee as part of a development opportunity. The committee is working well - Feedback from the Chair of the RDSC shows that we have fresh voices which add to the quality of the debate and make for stronger outcomes within the committee. LBU took the decision to not participate in CEDARS 2020/21 as the Development & Training programme had just transferred to a new team within the service in October 2020. The development programme was redeveloped as part of that transfer, it was then agreed that due to the lack of time for the new programme to be embedded it would therefore be beneficial to wait a year and then undertake the CEDARS survey in 2023.
7.3 | A Steering Group with a membership consisting of the Associate Director of HR or nominee, Director of Research and Enterprise or nominee, two colleagues from Research and Enterprise Services, representation from the schools which will include ECRs and Fixed Term academics. This Group will work with other Groups across the University and review the needs and subsequent actions on an annual basis. | HR/Graduate School/Research and Enterprise Services/Schools | 2021-01-01 | The Steering Group formed and serviced jointly by a representative of the Research and Enterprise Services and HR. 70% representation from Schools. |  | In progress | New steering group to be created Our Research and Enterprise Committee is updated on the progress against our actions on an annual basis. Additionally, a working group of action owners meets quarterly – as does a working group with oversight of the Development and Training programme (which consists of colleagues from R&E services, the Library and an enterprise-active academic.) As part of the development of the R&E Research and Knowledge Exchange Academy, a steering group will be created which will include Deans, DoRs, the Director of R&E and Associate Director of KE to have oversight of its strategic direction. Once created, it is proposed that the working group will be updated to support the ongoing development of the academy - and that the working group will be made up of a cross section of staff from across the university, including ECRs, Mid-career and experienced researchers.
Note on H19: check satisfaction rate with Kim, check number of funding applications from writing workshops with RDMs and any other statistics they might wish to add to give it more weight....if we can confirm 5% increrase in applications from over past two years then even better!